## Sayfa1
PROJECT PLAN AND GANTT CHART
|  | END WEEK | OVERALL PROGRESS
|  | 19 | 0%
PARALLEL?
TASKS | RESPONSIBLE | Week | STATUS | START | END | ST3 | ST2 | ST1
Determine Problems | Resp 1 | 3 | Not started | 0 | 3 | 0 | 0 | 3
Evaluate The System | Resp 2 | 1 | Not started | 3 | 4 | 0 | 0 | 1
Define Necessaries | Resp 3 | 2 | Not started | 4 | 6 | 0 | 0 | 2
The Company Necessaries | Resp 4 | 1 | Not started | 4 | 5 | 0 | 0 | 1
Engineer and Workers Necessaries | Resp 5 | 1 | Not started | 5 | 6 | 0 | 0 | 1
Determine Areas for Project | Resp 6 | 1 | Not started | 6 | 7 | 0 | 0 | 1
Literature Research | Resp 7 | 4 | Not started | 6 | 10 | 0 | 0 | 4
Research Same Graduation Projects for Guidline | Resp 8 | 2 | Not started | 6 | 8 | 0 | 0 | 2
Obtain Data and Knowledge About Industry | Resp 9 | 4 | Not started | 10 | 14 | 0 | 0 | 4
Collect Data From Manufacturing in Factory | Resp 10 | 2 | Not started | 10 | 12 | 0 | 0 | 2
Obtain Materials and How They Are Going to Combine Together | Resp 11 | 2 | Not started | 10 | 12 | 0 | 0 | 2
Meeting with Company Advisiors Engineers | Resp 12 | 2 | Not started | 12 | 14 | 0 | 0 | 2
Getting Feedback on Current System | Resp 13 | 1 | Not started | 12 | 13 | 0 | 0 | 1
Information About Production on Our Part | Resp 14 | 1 | Not started | 12 | 13 | 0 | 0 | 1
Develop Project Plan | Resp 15 | 9 | Not started | 13 | 22 | 0 | 0 | 9
Create a Schedule | Resp 16 | 3 | Not started | 13 | 16 | 0 | 0 | 3
Identify Task | Task 17 | 6 | Not started | 16 | 22 | 0 | 0 | 6
Create a Task Table | Task 18 | 3 | Not started | 16 | 19 | 0 | 0 | 3
Set Meetings | Task 19 | 3 | Not started | 16 | 19 | 0 | 0 | 3

## Sayfa2
| Project Name | Project Durat | Start Date | End date
| Asansörlü Çeki Komple | 207 | 2019-10-07 | 2020-05-01
Task ID | Task Description | Task Duration (DAY) | Start Date | End Date | 2019-10-07 | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 | 2019-12-23 | 2019-12-30 | 2020-01-06 | 2020-01-13 | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25
1 | Determine Problems | 7 | 2019-10-07 | 2019-10-14 | X | X
2 | Evaluate The System | 7 | 2019-10-15 | 2019-10-22 |  |  | X
3 | Define Necessaries | 7 | 2019-10-23 | 2019-10-30 |  |  |  | X
4 | The Company Necessaries | 6 | 2019-10-31 | 2019-11-06 |  |  |  |  | X
5 | Engineer and Workers Nec. | 4 | 2019-11-07 | 2019-11-11 | [5 empty] | X
6 | Determine Areas for Project | 7 | 2019-11-12 | 2019-11-19 | [6 empty] | X
7 | Literature Research | 30 | 2019-11-20 | 2019-12-20 | [7 empty] | X | X | X | X
8 | Research Same Graduation Proj. | 7 | 2019-12-21 | 2019-12-28 | [11 empty] | X
9 | Obtain Data and Knowledge | 14 | 2019-12-29 | 2020-01-12 | [12 empty] | X | X
10 | Collect Data From Manufac. | 6 | 2020-01-13 | 2020-01-19 | [14 empty] | X
11 | Obtain Materials | 4 | 2020-01-20 | 2020-01-24 | [15 empty] | X
12 | Meeting with Company Advisiors | 7 | 2020-01-25 | 2020-02-01 | [16 empty] | X
13 | Getting Feedback on Current | 6 | 2020-02-02 | 2020-02-08 | [17 empty] | X
14 | Information About Production | 7 | 2020-02-09 | 2020-02-16 | [18 empty] | X
15 | Develop Project Plan | 21 | 2020-02-17 | 2020-03-09 | [19 empty] | X | X | X | X
16 | Create a Schedule | 7 | 2020-03-10 | 2020-03-17 | [23 empty] | X
17 | Identify Task | 21 | 2020-03-18 | 2020-04-08 | [24 empty] | X | X | X
18 | Create a Task Table | 7 | 2020-04-09 | 2020-04-16 | [27 empty] | X
19 | Set Meetings | 14 | 2020-04-17 | 2020-05-01 | [28 empty] | X | X
Formulas:
Start Date = [End date, row above]+1
End date = [Start Date]+[Project Durat]