## Project Plan and Gantt Draft
PROJECT PLAN AND GANTT CHART
|  | END WEEK | OVERALL PROGRESS
|  | 19 | 0%
PARALLEL?
TASKS | RESPONSIBLE | WEEKS | STATUS | START | END | ST3 | ST2 | ST1
Determine Problems | Resp 1 | 3 | Not started | 0 | 3 | 0 | 0 | 3
Evaluate The System | Resp 2 | 1 | Not started | 3 | 4 | 0 | 0 | 1
Define Necessaries | Resp 3 | 2 | Not started | 4 | 6 | 0 | 0 | 2
The Company Necessaries | Resp 4 | 1 | Not started | 4 | 5 | 0 | 0 | 1
Engineer and Workers Necessaries | Resp 5 | 1 | Not started | 5 | 6 | 0 | 0 | 1
Determine Areas for Project | Resp 6 | 1 | Not started | 6 | 7 | 0 | 0 | 1
Literature Research | Resp 7 | 4 | Not started | 6 | 10 | 0 | 0 | 4
Research Same Graduation Projects for Guidline | Resp 8 | 2 | Not started | 6 | 8 | 0 | 0 | 2
Obtain Data and Knowledge About Industry | Resp 9 | 4 | Not started | 10 | 14 | 0 | 0 | 4
Collect Data From Manufacturing in Factory | Resp 10 | 2 | Not started | 10 | 12 | 0 | 0 | 2
Obtain Materials and How They Are Going to Combine Together | Resp 11 | 2 | Not started | 10 | 12 | 0 | 0 | 2
Meeting with Company Advisiors Engineers | Resp 12 | 2 | Not started | 12 | 14 | 0 | 0 | 2
Getting Feedback on Current System | Resp 13 | 1 | Not started | 12 | 13 | 0 | 0 | 1
Information About Production on Our Part | Resp 14 | 1 | Not started | 12 | 13 | 0 | 0 | 1
Develop Project Plan | Resp 15 | 9 | Not started | 13 | 22 | 0 | 0 | 9
Create a Schedule | Resp 16 | 3 | Not started | 13 | 16 | 0 | 0 | 3
Identify Task | Task 17 | 6 | Not started | 16 | 22 | 0 | 0 | 6
Create a Task Table | Task 18 | 3 | Not started | 16 | 19 | 0 | 0 | 3
Set Meetings | Task 19 | 3 | Not started | 16 | 19 | 0 | 0 | 3

## Project Plan and Gantt 2
[Project Name] Project Schedule
|  | Project Start Date | 2019-10-14 |  |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
|  | Project Lead | [8 empty] | 2019-10-14 | [6 empty] | 2019-10-21 | [6 empty] | 2019-10-28 | [6 empty] | 2019-11-04 | [6 empty] | 2019-11-11 | [6 empty] | 2019-11-18 | [6 empty] | 2019-11-25 | [6 empty] | 2019-12-02
 | time axis 2019-10-14 to 2019-12-08
OVERALL % | WBS | TASK | LEAD | START | END | PARALLEL WITH | DAYS | WEEKS | % DONE | WORK DAYS | time axis 2019-10-14 to 2019-12-08
5.263% | 1
| 1.1 |  |  | 2019-10-14 | 2019-03-06 |  |  |  | 100% | -159
| 1.2 |  |  | 2019-10-21 | 2019-02-22 |  |  |  | 0% | -172
| 1.3 |  |  | 2019-10-28 | 2019-03-15 |  |  |  | 0% | -162
| 1.4 |  |  | 2019-11-04 | 2019-02-25 |  |  |  | 0% | -181
| 1.5 |  |  | 2019-11-11 | 2019-03-05 |  |  |  | 0% | -180
| 1.6 |  |  | 2019-11-18 | 2019-03-15 |  |  |  | 0% | -177
| 1.7 |  |  | 2019-11-25 | 2019-02-28 |  |  |  | 0% | -193
| 1.8 |  |  | 2019-12-02 | 2019-04-05 |  |  |  | 0% | -172
| 1.9 |  |  | 2019-12-09 | 2019-04-29 |  |  |  | 0% | -161
| 1.10 |  |  | 2019-12-16 | 2019-05-07 |  |  |  | 0% | -160
| 1.11 |  |  | 2019-12-23 | 2019-03-05 |  |  |  | 0% | -210
| 1.12 |  |  | 2019-12-30 | 2019-03-06 |  |  |  | 0% | -214
| 1.13 |  |  | 2020-01-06 | 2019-04-11 |  |  |  | 0% | -193
| 1.14 |  |  | 2020-01-13 | 2019-04-11 |  |  |  | 0% | -198
| 1.15 |  |  | 2020-01-20 | 2019-05-23 |  |  |  | 0% | -173
| 1.16 |  |  | 2020-01-27 | 2019-05-30 |  |  |  | 0% | -173
| 1.17 |  |  | 2020-02-03 | 2019-06-21 |  |  |  | 0% | -162
| 1.18 |  |  | 2020-02-10 | 2019-03-05 |  |  |  | 0% | -245
| 1.19 |  |  | 2020-02-17 | 2019-05-23 |  |  |  | 0% | -193
0% | 2
| 2.1 |  |  | 2019-02-22 | 2019-02-22 |  |  |  | 0% | 1
| 2.2 |  |  | 2019-02-25 | 2019-03-04 |  |  |  | 0% | 6
| 2.3 |  |  | 2019-03-05 | 2019-03-07 |  |  |  | 0% | 3
| 2.4 |  |  | 2019-04-09 | 2019-04-17 |  |  |  | 0% | 7
| 2.5 |  |  | 2019-02-08 | 2019-04-17 |  |  |  | 0% | 49
| 2.6 |  |  | 2019-03-19 | 2019-04-04 |  |  |  | 0% | 13
| 2.7 |  |  | 2019-02-21 | 2019-02-21 |  |  |  | 0% | 1
| 2.8 |  |  | 2019-02-22 | 2019-03-15 |  |  |  | 0% | 16
| 2.9 |  |  | 2019-03-15 | 2019-04-11 |  |  |  | 0% | 20
| 2.10 |  |  | 2019-04-15 | 2019-04-15 |  |  |  | 0% | 1
| 2.11 |  |  | 2019-04-16 | 2019-05-10 |  |  |  | 0% | 19
| 2.12 |  |  | 2019-04-22 | 2019-04-26 |  |  |  | 0% | 5
| 2.13 |  |  | 2019-04-29 | 2019-04-29 |  |  |  | 0% | 1
| 2.14 |  |  | 2019-04-29 | 2019-05-03 |  |  |  | 0% | 5
| 2.15 |  |  | 2019-06-17 | 2019-06-28 |  |  |  | 0% | 10
| 2.16 |  |  | 2019-07-01 | 2019-07-05 |  |  |  | 0% | 5
| 2.17 |  |  | 2019-07-01 | 2019-07-05 |  |  |  | 0% | 5
| 2.18 |  |  | 2019-07-08 | 2019-07-12 |  |  |  | 0% | 5
| 2.19 |  |  | 2019-05-13 | 2019-05-13 |  |  |  | 0% | 1
| 2.20 |  |  | 2019-05-13 | 2019-05-13 |  |  |  | 0% | 1
| 2.21 |  |  | 2019-03-14 | 2019-03-28 |  |  |  | 0% | 11
| 2.22 |  |  | 2019-03-29 | 2019-03-29 |  |  |  | 0% | 1
| 2.23 |  |  | 2019-04-01 | 2019-05-02 |  |  |  | 0% | 24
| 2.24 |  |  | 2019-05-03 | 2019-05-03 |  |  |  | 0% | 1
| 2.25 |  |  | 2019-05-06 | 2019-05-13 |  |  |  | 0% | 6
| 2.26 |  |  | 2019-05-14 | 2019-06-14 |  |  |  | 0% | 24
| 2.27 |  |  | 2019-05-02 | 2019-05-02 |  |  |  | 0% | 1
| 2.28 |  |  | 2019-05-02 | 2019-06-06 |  |  |  | 0% | 26
| 2.29 |  |  | 2019-05-02 | 2019-05-03 |  |  |  | 0% | 2
| 2.30 |  |  | 2019-05-02 | 2019-06-03 |  |  |  | 0% | 23
| 2.31 |  |  | 2019-05-30 | 2019-05-30 |  |  |  | 0% | 1
| 2.32 |  |  | 2019-05-30 | 2019-05-30 |  |  |  | 0% | 1
| 2.33 |  |  | 2019-06-06 | 2019-06-19 |  |  |  | 0% | 10
| 2.34 |  |  | 2019-06-17 | 2019-07-05 |  |  |  | 0% | 15
| 2.35 |  |  | 2019-07-08 | 2019-07-12 |  |  |  | 0% | 5
| 2.36 |  |  | 2019-05-13 | 2019-05-13 |  |  |  | 0% | 1
| 2.37 |  |  | 2019-05-14 | 2019-06-21 |  |  |  | 0% | 29
| 2.38 |  |  | 2019-07-08 | 2019-07-22 |  |  |  | 0% | 11
| 2.39 |  |  | 2019-07-31 | 2019-07-31 |  |  |  | 0% | 1
| 2.40 |  |  | 2019-07-23 | 2019-08-06 |  |  |  | 0% | 11
| 2.41 |  |  | 2019-08-07 | 2019-08-12 |  |  |  | 0% | 4
| 2.42 |  |  | 2019-03-17 | 2019-03-21 |  |  |  | 0% | 4
| 2.43 |  |  | 2019-04-17 | 2019-07-17 |  |  |  | 0% | 66
| 2.44 |  |  | 2019-08-13 | 2019-08-16 |  |  |  | 0% | 4
| 2.45 |  |  | 2019-08-19 | 2019-08-28 |  |  |  | 0% | 8
| 2.46 |  |  | 2019-08-28 | 2019-08-28 |  |  |  | 0% | 1
| 2.47 |  |  | 2019-08-28 | 2019-09-24 |  |  |  | 0% | 20
| 2.48 |  |  | 2019-09-25 | 2019-09-25 |  |  |  | 0% | 1
| 2.49 |  |  | 2019-02-22 | 2019-04-10 |  |  |  | 0% | 34
| 2.50 |  |  | 2019-05-01 | 2019-05-15 |  |  |  | 0% | 11
| 2.51 |  |  | 2019-03-26 | 2019-03-26 |  |  |  | 0% | 1
| 2.52 |  |  | 2019-04-11 | 2019-04-17 |  |  |  | 0% | 5
| 2.53 |  |  | 2019-04-18 | 2019-04-24 |  |  |  | 0% | 5
| 2.54 |  |  | 2019-04-25 | 2019-05-15 |  |  |  | 0% | 15
| 2.55 |  |  | 2019-06-10 | 2019-10-30 |  |  |  | 0% | 103
| 2.56 |  |  | 2019-06-14 | 2019-06-14 |  |  |  | 0% | 1
| 2.57 |  |  | 2019-06-17 | 2019-07-05 |  |  |  | 0% | 15
| 2.58 |  |  | 2019-06-17 | 2019-06-28 |  |  |  | 0% | 10
| 2.59 |  |  | 2019-07-01 | 2019-07-09 |  |  |  | 0% | 7
| 2.60 |  |  | 2019-07-10 | 2019-07-12 |  |  |  | 0% | 3
| 2.61 |  |  | 2019-07-15 | 2019-08-06 |  |  |  | 0% | 17
0% | 3
| 3.1 |  |  | 2019-02-21 | 2019-02-21 |  |  |  | 0% | 1
| 3.2 |  |  | 2019-02-25 | 2019-02-27 |  |  |  | 0% | 3
| 3.3 |  |  | 2019-03-04 | 2019-03-08 |  |  |  | 0% | 5
| 3.4 |  |  | 2019-03-11 | 2019-03-13 |  |  |  | 0% | 3
| 3.5 |  |  | 2019-03-14 | 2019-03-27 |  |  |  | 0% | 10
| 3.6 |  |  | 2019-02-28 | 2019-02-28 |  |  |  | 0% | 1
| 3.7 |  |  | 2019-03-20 | 2019-03-28 |  |  |  | 0% | 7
| 3.8 |  |  | 2019-02-22 | 2019-02-27 |  |  |  | 0% | 4
| 3.9 |  |  | 2019-02-22 | 2019-03-18 |  |  |  | 0% | 17
| 3.10 |  |  | 2019-03-04 | 2019-03-08 |  |  |  | 0% | 5
| 3.11 |  |  | 2019-03-18 | 2019-03-18 |  |  |  | 0% | 1
| 3.12 |  |  | 2019-03-19 | 2019-03-20 |  |  |  | 0% | 2
| 3.13 |  |  | 2019-03-21 | 2019-04-03 |  |  |  | 0% | 10
| 3.14 |  |  | 2019-04-04 | 2019-04-10 |  |  |  | 0% | 5
| 3.15 |  |  | 2019-03-11 | 2019-03-15 |  |  |  | 0% | 5
| 3.16 |  |  | 2019-03-26 | 2019-04-08 |  |  |  | 0% | 10
| 3.17 |  |  | 2019-04-09 | 2019-04-30 |  |  |  | 0% | 16
| 3.18 |  |  | 2019-05-01 | 2019-05-07 |  |  |  | 0% | 5
| 3.19 |  |  | 2019-02-22 | 2019-03-21 |  |  |  | 0% | 20
| 3.20 |  |  | 2019-05-13 | 2019-05-17 |  |  |  | 0% | 5
| 3.21 |  |  | 2019-05-20 | 2019-07-12 |  |  |  | 0% | 40
| 3.22 |  |  | 2019-03-18 | 2019-03-18 |  |  |  | 0% | 1
| 3.23 |  |  | 2019-03-21 | 2019-03-22 |  |  |  | 0% | 2
| 3.24 |  |  | 2019-05-15 | 2019-05-15 |  |  |  | 0% | 1
| 3.25 |  |  | 2019-05-15 | 2019-05-23 |  |  |  | 0% | 7
| 3.26 |  |  | 2019-03-22 | 2019-04-01 |  |  |  | 0% | 7
| 3.27 |  |  | 2019-04-11 | 2019-04-11 |  |  |  | 0% | 1
| 3.28 |  |  | 2019-04-08 | 2019-05-08 |  |  |  | 0% | 23
| 3.29 |  |  | 2019-03-25 | 2019-04-11 |  |  |  | 0% | 14
| 3.30 |  |  | 2019-04-12 | 2019-04-18 |  |  |  | 0% | 5
| 3.31 |  |  | 2019-04-19 | 2019-05-16 |  |  |  | 0% | 20
| 3.32 |  |  | 2019-05-17 | 2019-05-23 |  |  |  | 0% | 5
| 3.33 |  |  | 2019-05-09 | 2019-05-23 |  |  |  | 0% | 11
| 3.34 |  |  | 2019-05-24 | 2019-06-13 |  |  |  | 0% | 15
| 3.35 |  |  | 2019-06-14 | 2019-06-20 |  |  |  | 0% | 5
| 3.36 |  |  | 2019-06-20 | 2019-07-31 |  |  |  | 0% | 30
| 3.37 |  |  | 2019-05-06 | 2019-05-10 |  |  |  | 0% | 5
| 3.38 |  |  | 2019-05-13 | 2019-07-26 |  |  |  | 0% | 55
| 3.39 |  |  | 2019-08-01 | 2019-08-21 |  |  |  | 0% | 15
| 3.40 |  |  | 2019-06-10 | 2019-06-14 |  |  |  | 0% | 5
| 3.41 |  |  | 2019-06-17 | 2019-07-19 |  |  |  | 0% | 25
| 3.42 |  |  | 2019-07-22 | 2019-08-05 |  |  |  | 0% | 11
| 3.43 |  |  | 2019-08-19 | 2019-08-30 |  |  |  | 0% | 10
| 3.44 |  |  | 2019-09-02 | 2019-09-02 |  |  |  | 0% | 1
| 3.45 |  |  | 2019-09-03 | 2019-09-24 |  |  |  | 0% | 16
| 3.46 |  |  | 2019-09-25 | 2019-09-25 |  |  |  | 0% | 1
0% | 4
| 4.1 |  |  | 2019-04-16 | 2019-04-24 |  |  |  | 0% | 7
| 4.2 |  |  | 2019-04-25 | 2019-04-25 |  |  |  | 0% | 1
| 4.3 |  |  | 2019-04-26 | 2019-05-27 |  |  |  | 0% | 22
| 4.4 |  |  | 2019-05-28 | 2019-06-21 |  |  |  | 0% | 19
| 4.5 |  |  | 2019-06-24 | 2019-06-27 |  |  |  | 0% | 4
| 4.6 |  |  | 2019-06-28 | 2019-07-31 |  |  |  | 0% | 24
| 4.7 |  |  | 2019-08-01 | 2019-08-06 |  |  |  | 0% | 4
| 4.8 |  |  | 2019-08-07 | 2019-09-09 |  |  |  | 0% | 24
| 4.9 |  |  | 2019-09-10 | 2019-09-17 |  |  |  | 0% | 6
| 4.10 |  |  | 2019-09-18 | 2019-10-18 |  |  |  | 0% | 23
| 4.11 |  |  | 2019-10-21 | 2019-11-01 |  |  |  | 0% | 10
| 4.12 |  |  | 2019-11-04 | 2019-11-14 |  |  |  | 0% | 9
| 4.13 |  |  | 2019-11-15 | 2019-12-02 |  |  |  | 0% | 12
| 4.14 |  |  | 2019-12-03 | 2019-12-03 |  |  |  | 0% | 1
0% | 5
| 5.1 |  |  | 2019-02-22 | 2019-02-22 |  |  |  | 0% | 1
| 5.2 |  |  | 2019-06-03 | 2019-06-14 |  |  |  | 0% | 10
| 5.3 |  |  | 2019-06-17 | 2019-06-21 |  |  |  | 0% | 5
| 5.4 |  |  | 2019-06-17 | 2019-06-21 |  |  |  | 0% | 5
| 5.5 |  |  | 2019-06-24 | 2019-07-12 |  |  |  | 0% | 15
| 5.6 |  |  | 2019-07-15 | 2019-07-19 |  |  |  | 0% | 5
| 5.7 |  |  | 2019-07-18 | 2019-08-09 |  |  |  | 0% | 17
| 5.8 |  |  | 2019-08-12 | 2019-08-23 |  |  |  | 0% | 10
| 5.9 |  |  | 2019-02-22 | 2019-02-22 |  |  |  | 0% | 1
| 5.10 |  |  | #VALUE! | #VALUE! |  |  |  | 0% | #VALUE!
| 5.11 |  |  | #VALUE! | #VALUE! |  |  |  | 0% | #VALUE!
| 5.12 |  |  | 2019-02-22 | 2019-02-22 |  |  |  | 0% | 1
Note on B6: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on C6: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on D6: Task Lead Enter the name of the Task Lead in this column.
Note on E6: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F6: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on H6: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on J6: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on K6: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.